## About
Rock Tracker
Version 2.4.0 · built 14 Oct 2026
Sheet | Purpose | Owner | Rows
RockTemplate | Copy this tab to add a rock (see Add a rock) | workbook owner
RocksEnd | Rock tabs live between RockTemplate and RocksEnd. Do not move, rename or delete this tab. | no one
Rocks | One row per rock tab: profile, latest update, key points and signals. Read only, stacked from row 2 of every rock tab | formula (no one types here)
Milestones | Every milestone of every active rock: commitment, dates, derived status, MC quarter and outlook flags. Read only, stacked from section 4 of every rock tab | formula (no one types here)
Risks | Every risk of every active rock on the 3 by 3 grid, with its key action. Read only, stacked from section 5 of every rock tab | formula (no one types here)
CallOuts | Call outs and upcoming events per active rock. Read only, stacked from section 6 of every rock tab | formula (no one types here)
Decisions | Decisions requested and the decision log in one table: raised by the lead before steerco (one line), outcome filled in on the same row after. Tab 1 shows the first 5 open requests per rock, tab 3.1 the open choice points, tab 5 the decided rows. Read only, stacked from section 7 of every rock tab | formula (no one types here)
Teams | Up to 5 teams per active rock with budgeted and actual positions and fill %. Read only, stacked from section 8 of every rock tab | formula (no one types here)
RockSnapshots | One row per active rock per snapshot, appended by the snapshot Office Script (Monday schedule or button) | Office Script snapshot.ts (no one types here)
MilestoneSnapshots | One row per milestone of an active rock per snapshot, appended by the snapshot Office Script | Office Script snapshot.ts (no one types here)
lkp_People | People at work role level: leads, GPMs. Dropdown for Lead and GPM | workbook owner
lkp_ValueChains | Value chains a rock belongs to: B2C, B2B, Trade, Assets, Enterprise. Dropdown for Value chain | workbook owner
lkp_Steercos | Steerco dates, entered once per quarter. Dropdown for Decisions.SteercoDate and source of NextSteerco | workbook owner
lkp_State | Rock states in order from best to worst (order is used by CheckCall) | architect
lkp_MilestoneStatus | The six milestone statuses (portal colours and email counts) | architect
lkp_LeadStatus | The only milestone statuses a lead sets by hand (Milestones.LeadStatus); the rest are calculated | architect
lkp_Commitment | Roadmap commitment levels, set by hand from the steerco outcome | architect
lkp_Level | Likelihood and impact levels of the 3 by 3 risk grid, in score order | architect
lkp_OpenClosed | Open or Closed for risks, call outs and decision follow ups | architect
lkp_YesNo | Yes or No for flags | architect
lkp_DecisionState | Decision row states (calculated) | architect
Checks
Check | OK when | Result
Rock tabs found | equals the number of rock tabs you expect | switched off
Duplicate rock IDs | 0 | switched off
Next steerco date missing | No | switched off
Choice point milestones without an open choice point decision | 0; otherwise raise the decision on the rock tab or change the milestone commitment (the Decisions row is authoritative for tab 3.1) | switched off
Open choice point decisions on rocks with no Choice point milestone | 0, unless the choice is not tied to a milestone | switched off
Completed milestones without an Actual date (warning) | 0 ideally; a warning only: the milestone still counts as Completed, add the date when you know it | switched off
Open decision requests beyond the 5 the portal shows | 0; otherwise the lead keeps at most 5 open requests per rock | switched off
Update guide
Your update, top to bottom on your rock tab only. Aim for 7 minutes per rock. Section 1, Rock profile, sits at the top and is set up once by the workbook owner; you start at section 2.
2. Update: set Update date to today (Ctrl+; types today), check State, rewrite Main message only if it changed, keep the 3 key risks or attention points current (one line each). The grey lines below them show the open decision requests from section 7.
3. Look at Signals (grey, calculated). If the data signal is worse than your State, either fix the data or say why in the main message.
4. Milestones: change Forecast date and Comment only where they moved. When a milestone is done, set Lead status to Completed and type the Actual date. Set Lead status to On hold or On watch when it applies; leave it empty otherwise. Progress %, a whole number from 0 to 100, is optional; Completed always shows 100%.
5. Risks: change only risks that changed. Closed risks: set Status to Closed.
6. Call outs: add new ones, set Status to Closed when done.
7. Decisions: add a row for each decision you need from steerco, one line each. After steerco, fill in Outcome, Owner and Follow up on the same row, and set commitment levels on your milestones. Never clear a decided row: it is the decision log.
8. Teams: change Budgeted or Actual only when a position is added, filled or left.
Everything else carries over: values stay in place until you change them. Grey cells are calculated; never type in them.
Add a rock
Add a rock (workbook owner, about 10 minutes):
1. Make sure the lead, the GPM and the value chain exist in lkp_People and lkp_ValueChains.
2. Right click the RockTemplate tab, Duplicate. Check the copy sits between RockTemplate and RocksEnd.
3. Rename the copy to a short name, for example R07 Checkout.
4. In section 1 Rock profile, fill in a new Rock ID (R plus two digits, never reused), name, value chain, lead, GPM, purpose, goals, what it delivers. Active is Yes.
5. Ask the lead to fill in sections 2 and 4 to 8. The portal shows the rock after its next refresh; nothing changes in the portal.
Close a rock
Close a rock: set Active to No in section 1. Its milestones, risks, call outs and teams leave the portal; its decisions stay in the decision log. Never delete the tab.
Rules
Type only on rock tabs, in the white cells. Grey cells are calculated. Never type on Rocks, Milestones, Risks, CallOuts, Decisions, Teams or the snapshot sheets.
Never insert or delete rows or columns on a rock tab, and never move a rock tab outside RockTemplate and RocksEnd.
Never reuse a Rock ID. Never rename RockTemplate, RocksEnd or any sheet other than a rock tab.
Pink cells are required and still empty.
Structure changes go through the factory repository (schema change, rebuild, migrate).
How the grey cells are calculated
Field | Plain explanation | Where
Open decision requests (type them in section 7; the portal shows the first 5) | How many decisions in section 7 are still waiting for an outcome. | Section 2 Update and steerco message
Decision requested 1 | The first open decision request from section 7; empty when there is none. | Section 2 Update and steerco message
Decision requested 2 | The second open decision request from section 7; empty when there is none. | Section 2 Update and steerco message
Decision requested 3 | The third open decision request from section 7; empty when there is none. | Section 2 Update and steerco message
Decision requested 4 | The fourth open decision request from section 7; empty when there is none. | Section 2 Update and steerco message
Decision requested 5 | The fifth open decision request from section 7; empty when there is none. | Section 2 Update and steerco message
Days since update | Number of days between today and the update date; empty when no update date is filled in. | Section 3 Signals
Data signal | What the data says: Off track when a committed milestone planned this MC quarter is now forecast after the quarter ends, At risk when a milestone has slipped, is overdue or a High risk has no action, otherwise On track. | Section 3 Signals
Check the call (data worse than State) | Yes when the data signal is worse than the State you chose, so the call is worth a second look. | Section 3 Signals
Outlook (current and next MC quarter) | The two MC quarters the counts below look at: the current one and the next one. | Section 3 Signals
Committed milestones in the outlook (y) | Milestones marked Committed with a date in the current or next MC quarter. | Section 3 Signals
of which Slipped (x) | Milestones in the current or next MC quarter whose forecast date is later than the planned date. | Section 3 Signals
of which On plan, On watch or Completed | Committed milestones in the current or next MC quarter that are On plan, On watch or Completed. | Section 3 Signals
of which Completed | Committed milestones in the current or next MC quarter that are Completed. | Section 3 Signals
Committed milestones overdue | Committed milestones that are not Completed or On hold and whose date has already passed. | Section 3 Signals
Open High risks | Risks that score High and are not Closed. | Section 3 Signals
High risks without key action or owner | Open High risks where the key action or the action owner is still empty. | Section 3 Signals
Positions budgeted (sum of teams) | Total budgeted positions over the teams in section 8. | Section 3 Signals
Positions actual (sum of teams) | Total actual positions over the teams in section 8. | Section 3 Signals
Fill % | Actual positions divided by budgeted positions; empty when nothing is budgeted. | Section 3 Signals
Key | Unique id made of the Rock ID, M and the row number; empty when the row has no title or the rock is not active. | Section 4 Milestones
Progress shown | The progress you typed, or 100 when the milestone is Completed. | Section 4 Milestones
Status | Completed or On hold when you set that, Not committed unless Commitment is Committed, Slipped when the forecast is later than planned, On watch when you flag it, otherwise On plan. | Section 4 Milestones
Slip (weeks) | Weeks between the planned date and the later forecast date, only when the milestone has slipped. | Section 4 Milestones
Slip severity | Major when the forecast moved into a later MC quarter than planned, Minor when it stays in the same quarter; empty unless slipped. | Section 4 Milestones
Timeline date (actual, else forecast, else planned) | The date the roadmap uses: the actual date, else the forecast date, else the planned date. | Section 4 Milestones
MC quarter | The MC quarter of the timeline date (the MC year starts in April). | Section 4 Milestones
Quarter ahead (1 to 4) | How many MC quarters ahead the timeline date is, 1 for the current quarter up to 4; an overdue milestone counts as 1. | Section 4 Milestones
In outlook (this and next MC quarter) | Yes when the planned date or the timeline date falls in the current or next MC quarter. | Section 4 Milestones
Shown in the portal | Yes when the portal should show it: dated within the next four MC quarters, not dated yet, or overdue; No once it was completed in the past. | Section 4 Milestones
Overdue | Yes when the milestone is Committed, not Completed or On hold, and its date has already passed. | Section 4 Milestones
Rock ID | Copied from the Rock ID in section 1. | Every list section
Rock | Copied from the rock name in section 1. | Every list section
GPM | Copied from the GPM in section 1. | Every list section
Key | Unique id made of the Rock ID, R and the row number; empty when the row has no title or the rock is not active. | Section 5 Risks
Score | Likelihood score times impact score, where Low is 1, Medium 2 and High 3. | Section 5 Risks
High | Yes when likelihood times impact scores 6 or more (Low 1, Medium 2, High 3), so High x Medium, Medium x High or High x High. | Section 5 Risks
Needs action | Yes when the risk is High, not closed, and the key action or the action owner is empty. | Section 5 Risks
Key | Unique id made of the Rock ID, C and the row number; empty when the row has no text or the rock is not active. | Section 6 Call outs
Key | Unique id made of the Rock ID, D and the row number; empty when the row has no decision text. | Section 7 Decisions
State | Requested while the outcome is empty, Decided once an outcome is filled in. | Section 7 Decisions
Open request no. | The position of this open request among the rock's open requests, counted from the top; empty once decided. | Section 7 Decisions
Due at next steerco | Yes when the request is still open and is raised for, or must be decided by, the next steerco. | Section 7 Decisions
Open follow up | Yes when the decision is made but its follow up is not Closed. | Section 7 Decisions
Key | Unique id made of the Rock ID, T and the row number; empty when the row has no team name or the rock is not active. | Section 8 Teams
Fill % | Actual positions divided by budgeted positions; empty when nothing is budgeted. | Section 8 Teams
Definitions
Term | Meaning | Group | What ends it
On track | All committed milestones are forecast on or before their planned date and no High risk is without an action | Rock state | Moves to At risk as soon as one of those stops being true
At risk | At least one committed milestone is slipping or a High risk is open, and the lead believes it is recoverable this quarter | Rock state | Back to On track when forecasts are back on plan; to Off track when not recoverable without a steerco decision
Off track | Commitments for this quarter will be missed without a steerco decision (scope, date or people) | Rock state | Leaves only after steerco has decided and the plan is re baselined
Completed | Done. Set by the lead (Lead status Completed); type the Actual date too. | Milestone status
On hold | Paused by decision. Set by the lead (Lead status). | Milestone status
Not committed | Calculated: commitment is Choice point or Not committed (or empty), and not Completed or On hold. | Milestone status
Slipped | Calculated: committed, and forecast date later than planned date. | Milestone status
On watch | Committed, forecast still on plan, but the lead flags a concern (Lead status On watch). | Milestone status
On plan | Calculated default: committed, forecast on or before planned date (or no forecast yet), no flag. | Milestone status
Start date | When work on the milestone starts or started. | Dates
Planned date | The date steerco committed to. Changes only when steerco re baselines. | Dates
Forecast date | The lead's current best estimate; the date leads update. Empty means on the planned date. | Dates
Actual date | The date the milestone was completed. Optional and recorded only: Lead status Completed is what makes it Completed. When filled in it is the timeline date. | Dates
MC quarter | Company quarter; the MC year starts in April. MC26Q3 is October to December 2026, MC26Q4 is January to March 2027, MC27Q1 is April to June 2027. A milestone's MC quarter follows its Actual date when filled in, else its Forecast date, else its Planned date. | Dates
Outlook | The current MC quarter plus the next one. Counts (x of y) use milestones with a planned or timeline date in the outlook. | Dates
Shown in the portal | A milestone shows on the roadmap when it falls in the outlook, has no date yet, or is not Completed and its date has passed (overdue). A Completed milestone whose actual date (or, when empty, planned date) is before today drops out. | Dates
Committed | Steerco has agreed to deliver this milestone by its planned date. | Commitment
Choice point | A decision (scope, date, funding or people) is needed before it can be committed. Raise it as a decision with Choice point Yes and a decide by date; that decision row is what the portal shows on tab 3.1. Set the milestone commitment to Choice point too; the About sheet flags rocks where the two disagree. | Commitment
Not committed | A known future need on the horizon, with no promise of date or scope. | Commitment
High risk | Very likely to impact the timeline: likelihood score times impact score is 6 or 9 (Low 1, Medium 2, High 3). | Risk
Key risks or attention points | Up to three one line points the lead wants steerco to see on tab 1. Free text; they replace the old Top risk flag. | Risk
Fill % | Actual positions divided by budgeted positions, per team and summed over the rock's teams. | Resourcing
Data signal | Off track when a committed milestone planned this MC quarter is forecast after its end; At risk when a committed milestone in the outlook slipped, a committed milestone is overdue, or a High risk has no key action or owner; otherwise On track. Shown next to the lead's State; the lead's State is what counts. | Signals

## RockTemplate
Section 1 Rock profile is set up once. Update top to bottom in about 7 minutes: 2 Update and key points, 3 check Signals, 4 Milestones that moved, 5 Risks that changed, 6 Call outs, 7 Decisions, 8 Teams when they change. White cells are yours; grey cells are calculated and the small grey text next to them says how.
1 Rock profile (workbook owner; lead may edit)
Rock ID (R plus two digits, never reused)
Rock name
Value chain
Initiative lead
GPM
| Active | Yes
Purpose
Goals
What it delivers
2 Update and steerco message (lead, every one or two weeks)
Update date
State
Main message (one or two lines)
Key risk or attention point 1 (one line)
Key risk or attention point 2 (one line)
Key risk or attention point 3 (one line)
| Open decision requests (type them in section 7; the portal shows the first 5) |  | How many decisions in section 7 are still waiting for an outcome.
| Decision requested 1 |  | The first open decision request from section 7; empty when there is none.
| Decision requested 2 |  | The second open decision request from section 7; empty when there is none.
| Decision requested 3 |  | The third open decision request from section 7; empty when there is none.
| Decision requested 4 |  | The fourth open decision request from section 7; empty when there is none.
| Decision requested 5 |  | The fifth open decision request from section 7; empty when there is none.
3 Signals (calculated, read only)
| Days since update |  | Number of days between today and the update date; empty when no update date is filled in.
| Data signal |  | What the data says: Off track when a committed milestone planned this MC quarter is now forecast after the quarter ends, At risk when a milestone has slipped, is overdue or a High risk has no action, otherwise On track.
| Check the call (data worse than State) |  | Yes when the data signal is worse than the State you chose, so the call is worth a second look.
| Outlook (current and next MC quarter) |  | The two MC quarters the counts below look at: the current one and the next one.
| Committed milestones in the outlook (y) |  | Milestones marked Committed with a date in the current or next MC quarter.
| of which Slipped (x) |  | Milestones in the current or next MC quarter whose forecast date is later than the planned date.
| of which On plan, On watch or Completed |  | Committed milestones in the current or next MC quarter that are On plan, On watch or Completed.
| of which Completed |  | Committed milestones in the current or next MC quarter that are Completed.
| Committed milestones overdue |  | Committed milestones that are not Completed or On hold and whose date has already passed.
| Open High risks |  | Risks that score High and are not Closed.
| High risks without key action or owner |  | Open High risks where the key action or the action owner is still empty.
| Positions budgeted (sum of teams) |  | Total budgeted positions over the teams in section 8.
| Positions actual (sum of teams) |  | Total actual positions over the teams in section 8.
| Fill % |  | Actual positions divided by budgeted positions; empty when nothing is budgeted.
4 Milestones (change only what moved)
Key | Milestone | Owner | Commitment | Start date | Planned date | Forecast date (empty = planned) | Actual date (when completed) | Lead status | Comment | Key result link | ADO id | ADO link (https, optional) | Description (what it enables, its value) | Detail 1 | Detail 2 | Detail 3 | Progress % | Progress shown | Status | Slip (weeks) | Slip severity | Timeline date (actual, else forecast, else planned) | MC quarter | Quarter ahead (1 to 4) | In outlook (this and next MC quarter) | Shown in the portal | Overdue | Rock ID | Rock | GPM
5 Risks (change only what changed)
Key | Risk | Likelihood | Impact | Key action | Action owner | Status (empty = Open) | Score | High | Needs action | Rock ID | Rock | GPM
6 Call outs (events and things steerco should know)
Key | Call out | Date (event or raised) | Status (empty = Open) | Rock ID | Rock | GPM
7 Decisions (one line each; raise before steerco, record the outcome on the same row after; this is the decision log)
Key | Decision requested (one line) | Steerco | Decide by | Choice point | Options (choice points) | Outcome (after steerco) | Follow up owner | Follow up (empty = Open) | State | Open request no. | Due at next steerco | Open follow up | Rock ID | Rock | GPM
8 Teams (lead, when positions change)
Key | Team | Team lead | Budgeted positions | Actual positions | Fill % | Rock ID | Rock | GPM
Formulas:
Shown in the portal = IF([Key]="","",IF(AND([Status]="Completed",IF(N([Actual date (when completed)])>0,N([Actual date (when completed)]),N([Planned date]))<TODAY()),"No",IF(OR(N(W48)=0,N([Quarter ahead (1 to 4)])>=1),"Yes","No")))
Overdue = IF([Key]="","",IF(AND([Commitment]="Committed",[Status]<>"Completed",[Status]<>"On hold",N(W48)>0,N(W48)<TODAY()),"Yes","No"))
Note on A47: Calculated, do not type here. Unique id made of the Rock ID, M and the row number; empty when the row has no title or the rock is not active.
Note on S47: Calculated, do not type here. The progress you typed, or 100 when the milestone is Completed.
Note on T47: Calculated, do not type here. Completed or On hold when you set that, Not committed unless Commitment is Committed, Slipped when the forecast is later than planned, On watch when you flag it, otherwise On plan.
Note on U47: Calculated, do not type here. Weeks between the planned date and the later forecast date, only when the milestone has slipped.
Note on V47: Calculated, do not type here. Major when the forecast moved into a later MC quarter than planned, Minor when it stays in the same quarter; empty unless slipped.
Note on W47: Calculated, do not type here. The date the roadmap uses: the actual date, else the forecast date, else the planned date.
Note on X47: Calculated, do not type here. The MC quarter of the timeline date (the MC year starts in April).
Note on Y47: Calculated, do not type here. How many MC quarters ahead the timeline date is, 1 for the current quarter up to 4; an overdue milestone counts as 1.
Note on Z47: Calculated, do not type here. Yes when the planned date or the timeline date falls in the current or next MC quarter.
Note on AA47: Calculated, do not type here. Yes when the portal should show it: dated within the next four MC quarters, not dated yet, or overdue; No once it was completed in the past.
Note on AB47: Calculated, do not type here. Yes when the milestone is Committed, not Completed or On hold, and its date has already passed.
Note on AC47: Calculated, do not type here. Copied from the Rock ID in section 1.
Note on AD47: Calculated, do not type here. Copied from the rock name in section 1.
Note on AE47: Calculated, do not type here. Copied from the GPM in section 1.
Note on A65: Calculated, do not type here. Unique id made of the Rock ID, R and the row number; empty when the row has no title or the rock is not active.
Note on H65: Calculated, do not type here. Likelihood score times impact score, where Low is 1, Medium 2 and High 3.
Note on I65: Calculated, do not type here. Yes when likelihood times impact scores 6 or more (Low 1, Medium 2, High 3), so High x Medium, Medium x High or High x High.
Note on J65: Calculated, do not type here. Yes when the risk is High, not closed, and the key action or the action owner is empty.
Note on K65: Calculated, do not type here. Copied from the Rock ID in section 1.
Note on L65: Calculated, do not type here. Copied from the rock name in section 1.
Note on M65: Calculated, do not type here. Copied from the GPM in section 1.
Note on A78: Calculated, do not type here. Unique id made of the Rock ID, C and the row number; empty when the row has no text or the rock is not active.
Note on E78: Calculated, do not type here. Copied from the Rock ID in section 1.
Note on F78: Calculated, do not type here. Copied from the rock name in section 1.
Note on G78: Calculated, do not type here. Copied from the GPM in section 1.
Note on A89: Calculated, do not type here. Unique id made of the Rock ID, D and the row number; empty when the row has no decision text.
Note on J89: Calculated, do not type here. Requested while the outcome is empty, Decided once an outcome is filled in.
Note on K89: Calculated, do not type here. The position of this open request among the rock's open requests, counted from the top; empty once decided.
Note on L89: Calculated, do not type here. Yes when the request is still open and is raised for, or must be decided by, the next steerco.
Note on M89: Calculated, do not type here. Yes when the decision is made but its follow up is not Closed.
Note on N89: Calculated, do not type here. Copied from the Rock ID in section 1.
Note on O89: Calculated, do not type here. Copied from the rock name in section 1.
Note on P89: Calculated, do not type here. Copied from the GPM in section 1.
Note on A117: Calculated, do not type here. Unique id made of the Rock ID, T and the row number; empty when the row has no team name or the rock is not active.
Note on F117: Calculated, do not type here. Actual positions divided by budgeted positions; empty when nothing is budgeted.
Note on G117: Calculated, do not type here. Copied from the Rock ID in section 1.
Note on H117: Calculated, do not type here. Copied from the rock name in section 1.
Note on I117: Calculated, do not type here. Copied from the GPM in section 1.

## RocksEnd
Rock tabs live between RockTemplate and RocksEnd. Do not move, rename or delete this tab.

## Rocks
RockID | RockName | ValueChain | Lead | GPM | Active | Purpose | Goals | Delivers | UpdateDate | State | MainMessage | Attention1 | Attention2 | Attention3 | UpdateAgeDays | Stale | MilestonesCommitted | MilestonesSlipped | MilestonesOnPlan | MilestonesCompleted | MilestonesOverdue | OpenHighRisks | HighRisksNoAction | PositionsBudgeted | PositionsActual | FillPct | DataSignal | CheckCall | CurrentMCQuarter | NextMCQuarter | ThirdMCQuarter | FourthMCQuarter

## Milestones
MilestoneKey | Title | Owner | Commitment | StartDate | PlannedDate | ForecastDate | ActualDate | LeadStatus | Comment | KRLink | ADOId | ADOLink | Description | Detail1 | Detail2 | Detail3 | Progress | ProgressShown | Status | SlipWeeks | SlipSeverity | TimelineDate | MCQuarter | QuarterAhead | InOutlook | Visible | Overdue | RockID | Rock | GPM

## Risks
RiskKey | Title | Likelihood | Impact | KeyAction | ActionOwner | RiskStatus | Score | High | NeedsAction | RockID | Rock | GPM

## CallOuts
CallOutKey | Text | Date | CallOutStatus | RockID | Rock | GPM

## Decisions
DecisionKey | Decision | SteercoDate | DecideBy | ChoicePoint | Options | Outcome | Owner | FollowUp | DecisionState | RequestNo | DueNextSteerco | OpenFollowUp | RockID | Rock | GPM

## Teams
TeamKey | TeamName | TeamLead | Budgeted | Actual | FillPct | RockID | Rock | GPM

## RockSnapshots
SnapshotID | SnapshotDate | RockID | Rock | GPM | UpdateDate | State | MainMessage | MilestonesCommitted | MilestonesSlipped | MilestonesCompleted | PositionsBudgeted | PositionsActual | OpenHighRisks

## MilestoneSnapshots
SnapshotID | SnapshotDate | MilestoneKey | RockID | Title | Commitment | PlannedDate | ForecastDate | ActualDate | MCQuarter | Status

## lkp_People
Name | Role

## lkp_ValueChains
Value
B2C
B2B
Trade
Assets
Enterprise

## lkp_Steercos
Date | Note
2026-10-21 | First steerco from the portal (assumed date, confirm)

## lkp_State
Value | Meaning
On track | All committed milestones are forecast on or before their planned date and no High risk is without an action
At risk | At least one committed milestone is slipping or a High risk is open, and the lead believes it is recoverable this quarter
Off track | Commitments for this quarter will be missed without a steerco decision (scope, date or people)

## lkp_MilestoneStatus
Value | Rule | SetBy
Completed | Lead status Completed (done) | Lead
On plan | Committed, forecast on or before planned date, no flag | Calculated
On watch | Committed, forecast on plan, lead flags a concern | Lead
Slipped | Committed, forecast later than planned date | Calculated
On hold | Paused by decision | Lead
Not committed | Commitment is Choice point or Not committed | Calculated

## lkp_LeadStatus
Value | Meaning
Completed | Done; type the Actual date too
On hold | Paused by decision
On watch | Forecast still on plan but you have a concern

## lkp_Commitment
Value | Meaning
Committed | Steerco has agreed to deliver this milestone by its planned date
Choice point | A decision (scope, date, funding or people) is needed before it can be committed
Not committed | A known future need on the horizon, with no promise of date or scope

## lkp_Level
Value | Score
Low | 1
Medium | 2
High | 3

## lkp_OpenClosed
Value
Open
Closed

## lkp_YesNo
Value
Yes
No

## lkp_DecisionState
Value | Meaning
Requested | Raised for steerco, no outcome yet
Decided | Outcome recorded after steerco