## About
Rock Tracker
Version 2.2.0 · built 14 Oct 2026
Sheet | Purpose | Owner | Rows
RockTemplate | Copy this tab to add a rock (see Add a rock) | workbook owner
RocksEnd | Rock tabs live between RockTemplate and RocksEnd. Do not move, rename or delete this tab. | no one
Rocks | One row per rock tab: profile, latest update, key points and signals. Read only, stacked from row 2 of every rock tab | formula (no one types here)
Milestones | Every milestone of every active rock: commitment, dates, derived status, MC quarter and outlook flags. Read only, stacked from section 3 of every rock tab | formula (no one types here)
Risks | Every risk of every active rock on the 3 by 3 grid, with its key action. Read only, stacked from section 4 of every rock tab | formula (no one types here)
CallOuts | Call outs and upcoming events per active rock. Read only, stacked from section 5 of every rock tab | formula (no one types here)
Decisions | Decisions requested and the decision log in one table: raised by the lead before steerco (one line), outcome filled in on the same row after. Tab 1 shows the first 5 open requests per rock, tab 3.1 the open choice points, tab 5 the decided rows. Read only, stacked from section 6 of every rock tab | formula (no one types here)
Teams | Up to 5 teams per active rock with budgeted and actual positions and fill %. Read only, stacked from section 8 of every rock tab | formula (no one types here)
RockSnapshots | One row per active rock per snapshot, appended by the snapshot Office Script (Monday schedule or button) | Office Script snapshot.ts (no one types here)
MilestoneSnapshots | One row per milestone of an active rock per snapshot, appended by the snapshot Office Script | Office Script snapshot.ts (no one types here)
lkp_People | People at work role level: leads, GPMs. Dropdown for Lead and GPM | workbook owner
lkp_ValueChains | Value chains or verticals a rock belongs to | workbook owner
lkp_Steercos | Steerco dates, entered once per quarter. Dropdown for Decisions.SteercoDate and source of NextSteerco | workbook owner
lkp_State | Rock states in order from best to worst (order is used by CheckCall) | architect
lkp_MilestoneStatus | The six milestone statuses (portal colours and email counts) | architect
lkp_LeadStatus | The only milestone statuses a lead sets by hand (Milestones.LeadStatus); the rest are calculated | architect
lkp_Commitment | Roadmap commitment levels, set by hand from the steerco outcome | architect
lkp_Level | Likelihood and impact levels of the 3 by 3 risk grid, in score order | architect
lkp_OpenClosed | Open or Closed for risks, call outs and decision follow ups | architect
lkp_YesNo | Yes or No for flags | architect
lkp_DecisionState | Decision row states (calculated) | architect
Checks
Check | OK when | Result
Rock tabs found | equals the number of rock tabs you expect
Duplicate rock IDs | 0
Next steerco date missing | No
Choice point milestones without an open choice point decision | 0; otherwise raise the decision on the rock tab or change the milestone commitment (the Decisions row is authoritative for tab 3.1)
Open choice point decisions on rocks with no Choice point milestone | 0, unless the choice is not tied to a milestone
Completed milestones without an Actual date (warning) | 0 ideally; a warning only: the milestone still counts as Completed, add the date when you know it
Open decision requests beyond the 5 the portal shows | 0; otherwise the lead keeps at most 5 open requests per rock
Update guide
Your update, top to bottom on your rock tab only. Aim for 7 minutes per rock.
1. Update: set Update date to today (Ctrl+; types today), check State, rewrite Main message only if it changed, keep the 3 key risks or attention points current (one line each). The grey lines below them show the open decision requests from section 6.
2. Look at Signals (grey, calculated). If the data signal is worse than your State, either fix the data or say why in the main message.
3. Milestones: change Forecast date and Comment only where they moved. When a milestone is done, set Lead status to Completed and type the Actual date. Set Lead status to On hold or On watch when it applies; leave it empty otherwise. Progress %, a whole number from 0 to 100, is optional; Completed always shows 100%.
4. Risks: change only risks that changed. Closed risks: set Status to Closed.
5. Call outs: add new ones, set Status to Closed when done.
6. Decisions: add a row for each decision you need from steerco, one line each. After steerco, fill in Outcome, Owner and Follow up on the same row, and set commitment levels on your milestones. Never clear a decided row: it is the decision log.
7. Teams: change Budgeted or Actual only when a position is added, filled or left.
Everything else carries over: values stay in place until you change them. Grey cells are calculated; never type in them.
Add a rock
Add a rock (workbook owner, about 10 minutes):
1. Make sure the lead, the GPM and the value chain exist in lkp_People and lkp_ValueChains.
2. Right click the RockTemplate tab, Duplicate. Check the copy sits between RockTemplate and RocksEnd.
3. Rename the copy to a short name, for example R07 Checkout.
4. In section 7 Rock profile, fill in a new Rock ID (R plus two digits, never reused), name, value chain, lead, GPM, purpose, goals, what it delivers. Active is Yes.
5. Ask the lead to fill in sections 1, 3 to 6 and 8. The portal shows the rock after its next refresh; nothing changes in the portal.
Close a rock
Close a rock: set Active to No in section 7. Its milestones, risks, call outs and teams leave the portal; its decisions stay in the decision log. Never delete the tab.
Rules
Type only on rock tabs, in the white cells. Grey cells are calculated. Never type on Rocks, Milestones, Risks, CallOuts, Decisions, Teams or the snapshot sheets.
Never insert or delete rows or columns on a rock tab, and never move a rock tab outside RockTemplate and RocksEnd.
Never reuse a Rock ID. Never rename RockTemplate, RocksEnd or any sheet other than a rock tab.
Pink cells are required and still empty.
Structure changes go through the factory repository (schema change, rebuild, migrate).
Definitions
Term | Meaning | Group | What ends it
On track | All committed milestones are forecast on or before their planned date and no High risk is without an action | Rock state | Moves to At risk as soon as one of those stops being true
At risk | At least one committed milestone is slipping or a High risk is open, and the lead believes it is recoverable this quarter | Rock state | Back to On track when forecasts are back on plan; to Off track when not recoverable without a steerco decision
Off track | Commitments for this quarter will be missed without a steerco decision (scope, date or people) | Rock state | Leaves only after steerco has decided and the plan is re baselined
Completed | Done. Set by the lead (Lead status Completed); type the Actual date too. | Milestone status
On hold | Paused by decision. Set by the lead (Lead status). | Milestone status
Not committed | Calculated: commitment is Choice point or Not committed (or empty), and not Completed or On hold. | Milestone status
Slipped | Calculated: committed, and forecast date later than planned date. | Milestone status
On watch | Committed, forecast still on plan, but the lead flags a concern (Lead status On watch). | Milestone status
On plan | Calculated default: committed, forecast on or before planned date (or no forecast yet), no flag. | Milestone status
Start date | When work on the milestone starts or started. | Dates
Planned date | The date steerco committed to. Changes only when steerco re baselines. | Dates
Forecast date | The lead's current best estimate; the date leads update. Empty means on the planned date. | Dates
Actual date | The date the milestone was completed. Optional and recorded only: Lead status Completed is what makes it Completed. When filled in it is the timeline date. | Dates
MC quarter | Company quarter; the MC year starts in April. MC26Q3 is October to December 2026, MC26Q4 is January to March 2027, MC27Q1 is April to June 2027. A milestone's MC quarter follows its Actual date when filled in, else its Forecast date, else its Planned date. | Dates
Outlook | The current MC quarter plus the next one. Counts (x of y) use milestones with a planned or timeline date in the outlook. | Dates
Shown in the portal | A milestone shows on the roadmap when it falls in the outlook, has no date yet, or is not Completed and its date has passed (overdue). A Completed milestone whose actual date (or, when empty, planned date) is before today drops out. | Dates
Committed | Steerco has agreed to deliver this milestone by its planned date. | Commitment
Choice point | A decision (scope, date, funding or people) is needed before it can be committed. Raise it as a decision with Choice point Yes and a decide by date; that decision row is what the portal shows on tab 3.1. Set the milestone commitment to Choice point too; the About sheet flags rocks where the two disagree. | Commitment
Not committed | A known future need on the horizon, with no promise of date or scope. | Commitment
High risk | Very likely to impact the timeline: likelihood score times impact score is 6 or 9 (Low 1, Medium 2, High 3). | Risk
Key risks or attention points | Up to three one line points the lead wants steerco to see on tab 1. Free text; they replace the old Top risk flag. | Risk
Fill % | Actual positions divided by budgeted positions, per team and summed over the rock's teams. | Resourcing
Data signal | Off track when a committed milestone planned this MC quarter is forecast after its end; At risk when a committed milestone in the outlook slipped, a committed milestone is overdue, or a High risk has no key action or owner; otherwise On track. Shown next to the lead's State; the lead's State is what counts. | Signals

## RockTemplate
Update top to bottom in about 7 minutes: 1 Update and key points, 2 check Signals, 3 Milestones that moved, 4 Risks that changed, 5 Call outs, 6 Decisions, 7 Teams when they change. White cells are yours; grey cells are calculated.
1 Update and steerco message (lead, every one or two weeks)
Update date
State
Main message (one or two lines)
Key risk or attention point 1 (one line)
Key risk or attention point 2 (one line)
Key risk or attention point 3 (one line)
Open decision requests (type them in section 6; the portal shows the first 5)
Decision requested 1
Decision requested 2
Decision requested 3
Decision requested 4
Decision requested 5
2 Signals (calculated, read only)
Days since update
Data signal
Check the call (data worse than State)
Outlook (current and next MC quarter)
Committed milestones in the outlook (y)
of which Slipped (x)
of which On plan, On watch or Completed
of which Completed
Committed milestones overdue
Open High risks
High risks without key action or owner
Positions budgeted (sum of teams)
Positions actual (sum of teams)
Fill %
3 Milestones (change only what moved)
Key | Milestone | Owner | Commitment | Start date | Planned date | Forecast date (empty = planned) | Actual date (when completed) | Lead status | Comment | Key result link | ADO id | ADO link (https, optional) | Description (what it enables, its value) | Detail 1 | Detail 2 | Detail 3 | Progress % | Progress shown | Status | Slip (weeks) | Timeline date (actual, else forecast, else planned) | MC quarter | In outlook (this and next MC quarter) | Shown in the portal | Overdue | Rock ID | Rock | GPM
4 Risks (change only what changed)
Key | Risk | Likelihood | Impact | Key action | Action owner | Status (empty = Open) | Score | High | Needs action | Rock ID | Rock | GPM
5 Call outs (events and things steerco should know)
Key | Call out | Date (event or raised) | Status (empty = Open) | Rock ID | Rock | GPM
6 Decisions (one line each; raise before steerco, record the outcome on the same row after; this is the decision log)
Key | Decision requested (one line) | Steerco | Decide by | Choice point | Options (choice points) | Outcome (after steerco) | Follow up owner | Follow up (empty = Open) | State | Open request no. | Due at next steerco | Open follow up | Rock ID | Rock | GPM
7 Rock profile (workbook owner; lead may edit)
Rock ID (R plus two digits, never reused)
Rock name
Value chain
Initiative lead
GPM
| Active | Yes
Purpose
Goals
What it delivers
8 Teams (lead, when positions change)
Key | Team | Team lead | Budgeted positions | Actual positions | Fill % | Rock ID | Rock | GPM
Formulas:
Shown in the portal = IF([Key]="","",IF([Status]="Completed",IF(IF(N([Actual date (when completed)])>0,N([Actual date (when completed)]),N([Planned date]))<TODAY(),"No",[In outlook (this and next MC quarter)]),IF(OR([In outlook (this and next MC quarter)]="Yes",N(V37)=0,N(V37)<TODAY()),"Yes","No")))
Overdue = IF([Key]="","",IF(AND([Commitment]="Committed",[Status]<>"Completed",[Status]<>"On hold",N(V37)>0,N(V37)<TODAY()),"Yes","No"))

## R01 Checkout Speed
Update top to bottom in about 7 minutes: 1 Update and key points, 2 check Signals, 3 Milestones that moved, 4 Risks that changed, 5 Call outs, 6 Decisions, 7 Teams when they change. White cells are yours; grey cells are calculated.
1 Update and steerco message (lead, every one or two weeks)
| Update date | 2026-10-12
| State | On track
| Main message (one or two lines) | One page checkout is in test and on plan. Saved payment methods are on watch while we wait for a vendor answer.
| Key risk or attention point 1 (one line) | Peak season freeze could block the release
| Key risk or attention point 2 (one line) | Wallet funding decision needed before Q4
Key risk or attention point 3 (one line)
Open decision requests (type them in section 6; the portal shows the first 5)
Decision requested 1
Decision requested 2
Decision requested 3
Decision requested 4
Decision requested 5
2 Signals (calculated, read only)
Days since update
Data signal
Check the call (data worse than State)
Outlook (current and next MC quarter)
Committed milestones in the outlook (y)
of which Slipped (x)
of which On plan, On watch or Completed
of which Completed
Committed milestones overdue
Open High risks
High risks without key action or owner
Positions budgeted (sum of teams)
Positions actual (sum of teams)
Fill %
3 Milestones (change only what moved)
Key | Milestone | Owner | Commitment | Start date | Planned date | Forecast date (empty = planned) | Actual date (when completed) | Lead status | Comment | Key result link | ADO id | ADO link (https, optional) | Description (what it enables, its value) | Detail 1 | Detail 2 | Detail 3 | Progress % | Progress shown | Status | Slip (weeks) | Timeline date (actual, else forecast, else planned) | MC quarter | In outlook (this and next MC quarter) | Shown in the portal | Overdue | Rock ID | Rock | GPM
| One page checkout | Lena Testfield | Committed | 2026-08-17 | 2026-11-30 | 2026-11-30 |  |  |  | KR 1.1 | ADO-1101 | https://ado.example.com/rocktracker/items/1101 | Single page that replaces the five step checkout. | Design signed off | Build in test | Release window to agree with ops | 60
| Saved payment methods | Omar Fictiv | Committed | 2026-09-01 | 2026-12-15 | 2026-12-10 |  | On watch | Vendor sandbox access still pending | KR 1.2 | ADO-1102 |  | Let returning customers pay with a stored method. | Vendor sandbox pending | Tokenisation design done |  | 30
| Address form speed up | Lena Testfield | Committed | 2026-08-03 | 2026-10-05 | 2026-10-02 | 2026-10-02 | Completed | Shipped 2 Oct | KR 1.1 | ADO-1103 |  | Autocomplete on the address form. | Shipped to all markets | Form time down by a third
| Wallet support | Marco Demoso | Choice point | [5 empty] | Needs a funding decision before we can commit | KR 1.3 | ADO-1104 |  | Pay with the phone wallet. | Funding decision open | Three options on the table
| Express pay button | Tove Nomen | Committed | 2026-09-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Completed | Went live today | KR 1.1 | ADO-1105 |  | A one tap pay button on the basket page. | Live on web | App follows later |  | 80
4 Risks (change only what changed)
Key | Risk | Likelihood | Impact | Key action | Action owner | Status (empty = Open) | Score | High | Needs action | Rock ID | Rock | GPM
| Payment vendor delays sandbox | Low | Low | Escalate through vendor manager | Lena Testfield
| Peak season freeze blocks release | Medium | High | Agree a release window with ops | Lena Testfield
| Legacy tax service times out | High | Medium | Cache rates; retired in Sept | Lena Testfield | Closed
5 Call outs (events and things steerco should know)
Key | Call out | Date (event or raised) | Status (empty = Open) | Rock ID | Rock | GPM
| Vendor review call | 2026-10-20
| Pricing page test results shared | 2026-09-30 | Closed
6 Decisions (one line each; raise before steerco, record the outcome on the same row after; this is the decision log)
Key | Decision requested (one line) | Steerco | Decide by | Choice point | Options (choice points) | Outcome (after steerco) | Follow up owner | Follow up (empty = Open) | State | Open request no. | Due at next steerco | Open follow up | Rock ID | Rock | GPM
| Fund wallet support this half | 2026-10-21 | 2026-10-21 | Yes | A: fund now. B: defer to next half. C: partner solution.
| Extend the vendor sandbox contract | 2026-10-21 | 2026-10-21
| Approve extra test devices | 2026-11-18 | 2026-11-18
| Keep the checkout at three steps | 2026-09-16 | 2026-09-16 |  |  | Agreed, three steps | Lena Testfield | Closed
| Move the release window before the freeze | 2026-11-18 | 2026-10-21
| Add a fraud check on express pay | 2026-11-18 | 2026-11-18
| Retire the old basket page | 2026-12-16 | 2026-12-16
7 Rock profile (workbook owner; lead may edit)
| Rock ID (R plus two digits, never reused) | R01
| Rock name | Checkout Speed
| Value chain | Checkout
| Initiative lead | Lena Testfield
| GPM | Priya Sampleton
| Active | Yes
| Purpose | Make paying take fewer steps so fewer baskets are abandoned.
| Goals | Cut checkout steps from 5 to 3. Lift completed baskets.
| What it delivers | One page checkout, saved payment methods, a faster address form.
8 Teams (lead, when positions change)
Key | Team | Team lead | Budgeted positions | Actual positions | Fill % | Rock ID | Rock | GPM
| Checkout Web | Mia Sandbox | 3 | 3
| Payments | Noor Testwell | 2 | 1
| Checkout Design | Jonas Mockley | 1 | 1
Formulas:
Shown in the portal = IF([Key]="","",IF([Status]="Completed",IF(IF(N([Actual date (when completed)])>0,N([Actual date (when completed)]),N([Planned date]))<TODAY(),"No",[In outlook (this and next MC quarter)]),IF(OR([In outlook (this and next MC quarter)]="Yes",N(V37)=0,N(V37)<TODAY()),"Yes","No")))
Overdue = IF([Key]="","",IF(AND([Commitment]="Committed",[Status]<>"Completed",[Status]<>"On hold",N(V37)>0,N(V37)<TODAY()),"Yes","No"))

## R02 Guided Onboarding
Update top to bottom in about 7 minutes: 1 Update and key points, 2 check Signals, 3 Milestones that moved, 4 Risks that changed, 5 Call outs, 6 Decisions, 7 Teams when they change. White cells are yours; grey cells are calculated.
1 Update and steerco message (lead, every one or two weeks)
| Update date | 2026-10-13
| State | At risk
| Main message (one or two lines) | Setup checklist slipped two weeks because design review ran long. Recoverable this quarter. Hiring is the bigger worry.
| Key risk or attention point 1 (one line) | Two engineering roles are still unfilled
| Key risk or attention point 2 (one line) | Setup checklist slipped two weeks
| Key risk or attention point 3 (one line) | Tips content not ready
Open decision requests (type them in section 6; the portal shows the first 5)
Decision requested 1
Decision requested 2
Decision requested 3
Decision requested 4
Decision requested 5
2 Signals (calculated, read only)
Days since update
Data signal
Check the call (data worse than State)
Outlook (current and next MC quarter)
Committed milestones in the outlook (y)
of which Slipped (x)
of which On plan, On watch or Completed
of which Completed
Committed milestones overdue
Open High risks
High risks without key action or owner
Positions budgeted (sum of teams)
Positions actual (sum of teams)
Fill %
3 Milestones (change only what moved)
Key | Milestone | Owner | Commitment | Start date | Planned date | Forecast date (empty = planned) | Actual date (when completed) | Lead status | Comment | Key result link | ADO id | ADO link (https, optional) | Description (what it enables, its value) | Detail 1 | Detail 2 | Detail 3 | Progress % | Progress shown | Status | Slip (weeks) | Timeline date (actual, else forecast, else planned) | MC quarter | In outlook (this and next MC quarter) | Shown in the portal | Overdue | Rock ID | Rock | GPM
| Setup checklist | Omar Fictiv | Committed | 2026-09-07 | 2026-11-20 | 2026-12-04 |  | On watch | Design review ran long | KR 2.1 | ADO-2201 |  | Guided list of the first five setup steps. | Design review ran long | Build starts next week |  | 25
| In app tips | Ines Samplewood | Committed | 2026-11-30 | 2027-01-31 |  |  | On hold | Paused until checklist ships | KR 2.2 | ADO-2202 |  | Short tips shown at the right moment. | Paused by decision | Content draft started |  | 40
| Starter templates | Omar Fictiv | Not committed | [5 empty] | Known need, no promise yet | KR 2.3 |  |  | Role based templates for a faster start. | Scope not agreed | Needs research input
| Role picker | Ravi Placeholder | Committed | 2026-10-05 | 2026-12-18 |  |  |  |  | KR 2.1 | ADO-2204 |  | Ask the role at signup and tailor the checklist. | Role list agreed | Build not started |  | 0
| Brand colour audit | Omar Fictiv | Committed | 2026-08-24 | 2026-09-18 |  |  | Completed | Done, actual date not typed | KR 2.1 | ADO-2205 |  | Check onboarding screens against the brand colours. | All screens reviewed | Fixes folded into checklist
4 Risks (change only what changed)
Key | Risk | Likelihood | Impact | Key action | Action owner | Status (empty = Open) | Score | High | Needs action | Rock ID | Rock | GPM
| Two engineering roles unfilled | High | High
| Tips content not ready | Medium | Medium | Draft with content team | Omar Fictiv
| Template licence unclear | Low | High | Legal review requested | Omar Fictiv
5 Call outs (events and things steerco should know)
Key | Call out | Date (event or raised) | Status (empty = Open) | Rock ID | Rock | GPM
| Design review moved to next week | 2026-10-15
6 Decisions (one line each; raise before steerco, record the outcome on the same row after; this is the decision log)
Key | Decision requested (one line) | Steerco | Decide by | Choice point | Options (choice points) | Outcome (after steerco) | Follow up owner | Follow up (empty = Open) | State | Open request no. | Due at next steerco | Open follow up | Rock ID | Rock | GPM
| Approve contractors for onboarding | 2026-11-18 | 2026-11-18
| Pause in app tips until checklist ships | 2026-09-16 | 2026-09-16 |  |  | Agreed, tips paused | Omar Fictiv | Open
7 Rock profile (workbook owner; lead may edit)
| Rock ID (R plus two digits, never reused) | R02
| Rock name | Guided Onboarding
| Value chain | Onboarding
| Initiative lead | Omar Fictiv
| GPM | Priya Sampleton
| Active | Yes
| Purpose | Help new users reach their first success in the first session.
| Goals | Raise week one activation. Halve time to first success.
| What it delivers | Setup checklist, in app tips, role based starter templates.
8 Teams (lead, when positions change)
Key | Team | Team lead | Budgeted positions | Actual positions | Fill % | Rock ID | Rock | GPM
| Growth Engineering | Kari Sampler | 1 | 1
| Content | Pim Fakeman | 1 | 0
| Product Design | Jonas Mockley | 1 | 1
| User Research | Sol Demoson | 1 | 0
Formulas:
Shown in the portal = IF([Key]="","",IF([Status]="Completed",IF(IF(N([Actual date (when completed)])>0,N([Actual date (when completed)]),N([Planned date]))<TODAY(),"No",[In outlook (this and next MC quarter)]),IF(OR([In outlook (this and next MC quarter)]="Yes",N(V37)=0,N(V37)<TODAY()),"Yes","No")))
Overdue = IF([Key]="","",IF(AND([Commitment]="Committed",[Status]<>"Completed",[Status]<>"On hold",N(V37)>0,N(V37)<TODAY()),"Yes","No"))

## R03 Same Day Fulfilment
Update top to bottom in about 7 minutes: 1 Update and key points, 2 check Signals, 3 Milestones that moved, 4 Risks that changed, 5 Call outs, 6 Decisions, 7 Teams when they change. White cells are yours; grey cells are calculated.
1 Update and steerco message (lead, every one or two weeks)
| Update date | 2026-09-25
| State | At risk
| Main message (one or two lines) | Carrier integration is now forecast for January. We believe the quarter can still be saved with extra people.
| Key risk or attention point 1 (one line) | Carrier certification is the critical path
Key risk or attention point 2 (one line)
Key risk or attention point 3 (one line)
Open decision requests (type them in section 6; the portal shows the first 5)
Decision requested 1
Decision requested 2
Decision requested 3
Decision requested 4
Decision requested 5
2 Signals (calculated, read only)
Days since update
Data signal
Check the call (data worse than State)
Outlook (current and next MC quarter)
Committed milestones in the outlook (y)
of which Slipped (x)
of which On plan, On watch or Completed
of which Completed
Committed milestones overdue
Open High risks
High risks without key action or owner
Positions budgeted (sum of teams)
Positions actual (sum of teams)
Fill %
3 Milestones (change only what moved)
Key | Milestone | Owner | Commitment | Start date | Planned date | Forecast date (empty = planned) | Actual date (when completed) | Lead status | Comment | Key result link | ADO id | ADO link (https, optional) | Description (what it enables, its value) | Detail 1 | Detail 2 | Detail 3 | Progress % | Progress shown | Status | Slip (weeks) | Timeline date (actual, else forecast, else planned) | MC quarter | In outlook (this and next MC quarter) | Shown in the portal | Overdue | Rock ID | Rock | GPM
| Carrier integration | Tove Nomen | Committed | 2026-08-31 | 2026-12-10 | 2027-01-14 |  |  | Carrier API certification took longer | KR 3.1 | ADO-3301 |  | Connect the two same day carriers. | Certification took longer | Extra people requested |  | 15
| Cut off time logic | Tove Nomen | Committed | 2026-11-02 | 2027-02-15 | 2027-02-15 |  |  |  | KR 3.1 | ADO-3302 |  | Order cut off times per region. | Rules drafted | Waits on carrier slots
| Delivery promise on product pages | Priya Sampleton | Committed | 2026-12-01 | 2027-03-10 |  |  |  |  | KR 3.2 | ADO-3303 |  | Show the same day promise on every product page. | Design not started | Depends on cut off logic
| Region one pilot | Omar Fictiv | Committed | 2026-07-20 | 2026-09-10 | 2026-09-10 |  |  | Pilot date passed, close out pending | KR 3.1 | ADO-3304 |  | Limited pilot in the first region. | Pilot ran for two weeks | Close out report open |  | 70
| Third region rollout | Tove Nomen | Committed | 2027-02-01 | 2027-04-20 |  |  |  |  | KR 3.2 | ADO-3305 |  | Extend same day delivery to a third region. | Starts after region two | Plan to be refined
4 Risks (change only what changed)
Key | Risk | Likelihood | Impact | Key action | Action owner | Status (empty = Open) | Score | High | Needs action | Rock ID | Rock | GPM
| Carrier capacity in peak weeks | High | Low | Reserve capacity early | Tove Nomen
| Address data quality | Medium | Low | Add validation | Tove Nomen
| Warehouse staffing | Low | Medium | Seasonal hiring plan | Tove Nomen
5 Call outs (events and things steerco should know)
Key | Call out | Date (event or raised) | Status (empty = Open) | Rock ID | Rock | GPM
| Carrier certification workshop | 2026-10-28
6 Decisions (one line each; raise before steerco, record the outcome on the same row after; this is the decision log)
Key | Decision requested (one line) | Steerco | Decide by | Choice point | Options (choice points) | Outcome (after steerco) | Follow up owner | Follow up (empty = Open) | State | Open request no. | Due at next steerco | Open follow up | Rock ID | Rock | GPM
| Add three people to carrier integration | 2026-11-18 | 2026-10-21
| Pick carrier for region two | 2026-09-16 | 2026-09-16 |  |  | Carrier B selected | Tove Nomen | Closed
7 Rock profile (workbook owner; lead may edit)
| Rock ID (R plus two digits, never reused) | R03
| Rock name | Same Day Fulfilment
| Value chain | Fulfilment
| Initiative lead | Tove Nomen
| GPM | Marco Demoso
| Active | Yes
| Purpose | Offer same day delivery in the two largest regions.
| Goals | Same day option live in two regions. Keep late deliveries under 3 percent.
| What it delivers | Carrier integration, cut off time logic, delivery promise on product pages.
8 Teams (lead, when positions change)
Key | Team | Team lead | Budgeted positions | Actual positions | Fill % | Rock ID | Rock | GPM
| Carrier Integration | Anya Notreal | 2 | 3
| Routing | Bo Samplestein | 1 | 1
| Cut Off Logic | Anya Notreal | 1 | 1
| Product Pages | Mia Sandbox | 1 | 0
Formulas:
Shown in the portal = IF([Key]="","",IF([Status]="Completed",IF(IF(N([Actual date (when completed)])>0,N([Actual date (when completed)]),N([Planned date]))<TODAY(),"No",[In outlook (this and next MC quarter)]),IF(OR([In outlook (this and next MC quarter)]="Yes",N(V37)=0,N(V37)<TODAY()),"Yes","No")))
Overdue = IF([Key]="","",IF(AND([Commitment]="Committed",[Status]<>"Completed",[Status]<>"On hold",N(V37)>0,N(V37)<TODAY()),"Yes","No"))

## R04 Loyalty Pilot
Update top to bottom in about 7 minutes: 1 Update and key points, 2 check Signals, 3 Milestones that moved, 4 Risks that changed, 5 Call outs, 6 Decisions, 7 Teams when they change. White cells are yours; grey cells are calculated.
1 Update and steerco message (lead, every one or two weeks)
Update date
| State | On track
| Main message (one or two lines) | Just started, details to follow.
Key risk or attention point 1 (one line)
Key risk or attention point 2 (one line)
Key risk or attention point 3 (one line)
Open decision requests (type them in section 6; the portal shows the first 5)
Decision requested 1
Decision requested 2
Decision requested 3
Decision requested 4
Decision requested 5
2 Signals (calculated, read only)
Days since update
Data signal
Check the call (data worse than State)
Outlook (current and next MC quarter)
Committed milestones in the outlook (y)
of which Slipped (x)
of which On plan, On watch or Completed
of which Completed
Committed milestones overdue
Open High risks
High risks without key action or owner
Positions budgeted (sum of teams)
Positions actual (sum of teams)
Fill %
3 Milestones (change only what moved)
Key | Milestone | Owner | Commitment | Start date | Planned date | Forecast date (empty = planned) | Actual date (when completed) | Lead status | Comment | Key result link | ADO id | ADO link (https, optional) | Description (what it enables, its value) | Detail 1 | Detail 2 | Detail 3 | Progress % | Progress shown | Status | Slip (weeks) | Timeline date (actual, else forecast, else planned) | MC quarter | In outlook (this and next MC quarter) | Shown in the portal | Overdue | Rock ID | Rock | GPM
| Points ledger | Ravi Placeholder | Committed
| Pilot group selection | Lena Testfield | Not committed
4 Risks (change only what changed)
Key | Risk | Likelihood | Impact | Key action | Action owner | Status (empty = Open) | Score | High | Needs action | Rock ID | Rock | GPM
| Fraud on points redemption | Medium |  | Add limits
Check with risk team
5 Call outs (events and things steerco should know)
Key | Call out | Date (event or raised) | Status (empty = Open) | Rock ID | Rock | GPM
6 Decisions (one line each; raise before steerco, record the outcome on the same row after; this is the decision log)
Key | Decision requested (one line) | Steerco | Decide by | Choice point | Options (choice points) | Outcome (after steerco) | Follow up owner | Follow up (empty = Open) | State | Open request no. | Due at next steerco | Open follow up | Rock ID | Rock | GPM
7 Rock profile (workbook owner; lead may edit)
| Rock ID (R plus two digits, never reused) | R04
| Rock name | Loyalty Pilot
| Value chain | Checkout
| Initiative lead | Ravi Placeholder
| GPM | Marco Demoso
| Active | Yes
| Purpose | Test a points scheme with a small group of returning customers.
Goals
What it delivers
8 Teams (lead, when positions change)
Key | Team | Team lead | Budgeted positions | Actual positions | Fill % | Rock ID | Rock | GPM
| Pilot squad |  | 0 | 1
Formulas:
Shown in the portal = IF([Key]="","",IF([Status]="Completed",IF(IF(N([Actual date (when completed)])>0,N([Actual date (when completed)]),N([Planned date]))<TODAY(),"No",[In outlook (this and next MC quarter)]),IF(OR([In outlook (this and next MC quarter)]="Yes",N(V37)=0,N(V37)<TODAY()),"Yes","No")))
Overdue = IF([Key]="","",IF(AND([Commitment]="Committed",[Status]<>"Completed",[Status]<>"On hold",N(V37)>0,N(V37)<TODAY()),"Yes","No"))

## R05 Legacy Returns
Update top to bottom in about 7 minutes: 1 Update and key points, 2 check Signals, 3 Milestones that moved, 4 Risks that changed, 5 Call outs, 6 Decisions, 7 Teams when they change. White cells are yours; grey cells are calculated.
1 Update and steerco message (lead, every one or two weeks)
| Update date | 2026-07-10
| State | On track
| Main message (one or two lines) | Closed after migration finished.
| Key risk or attention point 1 (one line) | Closed after migration finished
Key risk or attention point 2 (one line)
Key risk or attention point 3 (one line)
Open decision requests (type them in section 6; the portal shows the first 5)
Decision requested 1
Decision requested 2
Decision requested 3
Decision requested 4
Decision requested 5
2 Signals (calculated, read only)
Days since update
Data signal
Check the call (data worse than State)
Outlook (current and next MC quarter)
Committed milestones in the outlook (y)
of which Slipped (x)
of which On plan, On watch or Completed
of which Completed
Committed milestones overdue
Open High risks
High risks without key action or owner
Positions budgeted (sum of teams)
Positions actual (sum of teams)
Fill %
3 Milestones (change only what moved)
Key | Milestone | Owner | Commitment | Start date | Planned date | Forecast date (empty = planned) | Actual date (when completed) | Lead status | Comment | Key result link | ADO id | ADO link (https, optional) | Description (what it enables, its value) | Detail 1 | Detail 2 | Detail 3 | Progress % | Progress shown | Status | Slip (weeks) | Timeline date (actual, else forecast, else planned) | MC quarter | In outlook (this and next MC quarter) | Shown in the portal | Overdue | Rock ID | Rock | GPM
| Migrate open returns | Ines Samplewood | Committed | 2026-03-02 | 2026-06-30 | 2026-06-28 | 2026-06-28 | Completed |  |  |  |  | Move all open returns to the new flow. | All open returns moved
4 Risks (change only what changed)
Key | Risk | Likelihood | Impact | Key action | Action owner | Status (empty = Open) | Score | High | Needs action | Rock ID | Rock | GPM
| Data loss on migration | Low | High | Dry run done | Ines Samplewood | Closed
5 Call outs (events and things steerco should know)
Key | Call out | Date (event or raised) | Status (empty = Open) | Rock ID | Rock | GPM
| Old portal switched off | 2026-07-01 | Closed
6 Decisions (one line each; raise before steerco, record the outcome on the same row after; this is the decision log)
Key | Decision requested (one line) | Steerco | Decide by | Choice point | Options (choice points) | Outcome (after steerco) | Follow up owner | Follow up (empty = Open) | State | Open request no. | Due at next steerco | Open follow up | Rock ID | Rock | GPM
| Close the legacy returns rock | 2026-09-16 | 2026-09-16 |  |  | Closed, no further work | Ines Samplewood | Closed
7 Rock profile (workbook owner; lead may edit)
| Rock ID (R plus two digits, never reused) | R05
| Rock name | Legacy Returns
| Value chain | Fulfilment
| Initiative lead | Ines Samplewood
| GPM | Marco Demoso
| Active | No
| Purpose | Retire the old returns portal.
| Goals | Single returns flow.
| What it delivers | Migration of open returns.
8 Teams (lead, when positions change)
Key | Team | Team lead | Budgeted positions | Actual positions | Fill % | Rock ID | Rock | GPM
| Returns | Ines Samplewood | 2 | 2
Formulas:
Shown in the portal = IF([Key]="","",IF([Status]="Completed",IF(IF(N([Actual date (when completed)])>0,N([Actual date (when completed)]),N([Planned date]))<TODAY(),"No",[In outlook (this and next MC quarter)]),IF(OR([In outlook (this and next MC quarter)]="Yes",N(V37)=0,N(V37)<TODAY()),"Yes","No")))
Overdue = IF([Key]="","",IF(AND([Commitment]="Committed",[Status]<>"Completed",[Status]<>"On hold",N(V37)>0,N(V37)<TODAY()),"Yes","No"))

## RocksEnd
Rock tabs live between RockTemplate and RocksEnd. Do not move, rename or delete this tab.

## Rocks
RockID | RockName | ValueChain | Lead | GPM | Active | Purpose | Goals | Delivers | UpdateDate | State | MainMessage | Attention1 | Attention2 | Attention3 | UpdateAgeDays | Stale | MilestonesCommitted | MilestonesSlipped | MilestonesOnPlan | MilestonesCompleted | MilestonesOverdue | OpenHighRisks | HighRisksNoAction | PositionsBudgeted | PositionsActual | FillPct | DataSignal | CheckCall | CurrentMCQuarter | NextMCQuarter

## Milestones
MilestoneKey | Title | Owner | Commitment | StartDate | PlannedDate | ForecastDate | ActualDate | LeadStatus | Comment | KRLink | ADOId | ADOLink | Description | Detail1 | Detail2 | Detail3 | Progress | ProgressShown | Status | SlipWeeks | TimelineDate | MCQuarter | InOutlook | Visible | Overdue | RockID | Rock | GPM

## Risks
RiskKey | Title | Likelihood | Impact | KeyAction | ActionOwner | RiskStatus | Score | High | NeedsAction | RockID | Rock | GPM

## CallOuts
CallOutKey | Text | Date | CallOutStatus | RockID | Rock | GPM

## Decisions
DecisionKey | Decision | SteercoDate | DecideBy | ChoicePoint | Options | Outcome | Owner | FollowUp | DecisionState | RequestNo | DueNextSteerco | OpenFollowUp | RockID | Rock | GPM

## Teams
TeamKey | TeamName | TeamLead | Budgeted | Actual | FillPct | RockID | Rock | GPM

## RockSnapshots
SnapshotID | SnapshotDate | RockID | Rock | GPM | UpdateDate | State | MainMessage | MilestonesCommitted | MilestonesSlipped | MilestonesCompleted | PositionsBudgeted | PositionsActual | OpenHighRisks
2026-09-28¦R01 | 2026-09-28 | R01 | Checkout Speed | Priya Sampleton | 2026-10-12 | On track | One page checkout is in test and on plan. Saved payment methods are on watch while we wait for a vendor answer. | 4 | 0 | 0 | 6 | 5 | 1
2026-09-28¦R02 | 2026-09-28 | R02 | Guided Onboarding | Priya Sampleton | 2026-10-13 | At risk | Setup checklist slipped two weeks because design review ran long. Recoverable this quarter. Hiring is the bigger worry. | 4 | 0 | 0 | 4 | 2 | 1
2026-09-28¦R03 | 2026-09-28 | R03 | Same Day Fulfilment | Marco Demoso | 2026-09-25 | At risk | Carrier integration is now forecast for January. We believe the quarter can still be saved with extra people. | 5 | 0 | 0 | 5 | 5 | 0
2026-09-28¦R04 | 2026-09-28 | R04 | Loyalty Pilot | Marco Demoso |  | On track | Just started, details to follow. | 1 | 0 | 0 | 0 | 1 | 0
2026-10-05¦R01 | 2026-10-05 | R01 | Checkout Speed | Priya Sampleton | 2026-10-12 | On track | One page checkout is in test and on plan. Saved payment methods are on watch while we wait for a vendor answer. | 4 | 0 | 0 | 6 | 5 | 1
2026-10-05¦R02 | 2026-10-05 | R02 | Guided Onboarding | Priya Sampleton | 2026-10-13 | At risk | Setup checklist slipped two weeks because design review ran long. Recoverable this quarter. Hiring is the bigger worry. | 4 | 1 | 0 | 4 | 2 | 1
2026-10-05¦R03 | 2026-10-05 | R03 | Same Day Fulfilment | Marco Demoso | 2026-09-25 | At risk | Carrier integration is now forecast for January. We believe the quarter can still be saved with extra people. | 5 | 0 | 0 | 5 | 5 | 0
2026-10-05¦R04 | 2026-10-05 | R04 | Loyalty Pilot | Marco Demoso |  | On track | Just started, details to follow. | 1 | 0 | 0 | 0 | 1 | 0
2026-10-12¦R01 | 2026-10-12 | R01 | Checkout Speed | Priya Sampleton | 2026-10-12 | On track | One page checkout is in test and on plan. Saved payment methods are on watch while we wait for a vendor answer. | 4 | 0 | 1 | 6 | 5 | 1
2026-10-12¦R02 | 2026-10-12 | R02 | Guided Onboarding | Priya Sampleton | 2026-10-13 | At risk | Setup checklist slipped two weeks because design review ran long. Recoverable this quarter. Hiring is the bigger worry. | 4 | 1 | 1 | 4 | 2 | 1
2026-10-12¦R03 | 2026-10-12 | R03 | Same Day Fulfilment | Marco Demoso | 2026-09-25 | At risk | Carrier integration is now forecast for January. We believe the quarter can still be saved with extra people. | 5 | 1 | 0 | 5 | 5 | 0
2026-10-12¦R04 | 2026-10-12 | R04 | Loyalty Pilot | Marco Demoso |  | On track | Just started, details to follow. | 1 | 0 | 0 | 0 | 1 | 0

## MilestoneSnapshots
SnapshotID | SnapshotDate | MilestoneKey | RockID | Title | Commitment | PlannedDate | ForecastDate | ActualDate | MCQuarter | Status
2026-09-28¦R01-M01 | 2026-09-28 | R01-M01 | R01 | One page checkout | Committed | 2026-11-30 | 2026-11-30 |  | MC26Q3 | On plan
2026-09-28¦R01-M02 | 2026-09-28 | R01-M02 | R01 | Saved payment methods | Committed | 2026-12-15 | 2026-12-10 |  | MC26Q3 | On watch
2026-09-28¦R01-M03 | 2026-09-28 | R01-M03 | R01 | Address form speed up | Committed | 2026-10-05 | 2026-10-02 |  | MC26Q3 | On plan
2026-09-28¦R01-M04 | 2026-09-28 | R01-M04 | R01 | Wallet support | Choice point |  |  |  |  | Not committed
2026-09-28¦R01-M05 | 2026-09-28 | R01-M05 | R01 | Express pay button | Committed | 2026-10-14 | 2026-10-14 |  | MC26Q3 | On plan
2026-09-28¦R02-M01 | 2026-09-28 | R02-M01 | R02 | Setup checklist | Committed | 2026-11-20 | 2026-11-20 |  | MC26Q3 | On watch
2026-09-28¦R02-M02 | 2026-09-28 | R02-M02 | R02 | In app tips | Committed | 2027-01-31 |  |  | MC26Q4 | On hold
2026-09-28¦R02-M03 | 2026-09-28 | R02-M03 | R02 | Starter templates | Not committed |  |  |  |  | Not committed
2026-09-28¦R02-M04 | 2026-09-28 | R02-M04 | R02 | Role picker | Committed | 2026-12-18 |  |  | MC26Q3 | On plan
2026-09-28¦R02-M05 | 2026-09-28 | R02-M05 | R02 | Brand colour audit | Committed | 2026-09-18 |  |  | MC26Q2 | On plan
2026-09-28¦R03-M01 | 2026-09-28 | R03-M01 | R03 | Carrier integration | Committed | 2026-12-10 | 2026-12-10 |  | MC26Q3 | On plan
2026-09-28¦R03-M02 | 2026-09-28 | R03-M02 | R03 | Cut off time logic | Committed | 2027-02-15 | 2027-02-15 |  | MC26Q4 | On plan
2026-09-28¦R03-M03 | 2026-09-28 | R03-M03 | R03 | Delivery promise on product pages | Committed | 2027-03-10 |  |  | MC26Q4 | On plan
2026-09-28¦R03-M04 | 2026-09-28 | R03-M04 | R03 | Region one pilot | Committed | 2026-09-10 | 2026-09-10 |  | MC26Q2 | On plan
2026-09-28¦R03-M05 | 2026-09-28 | R03-M05 | R03 | Third region rollout | Committed | 2027-04-20 |  |  | MC27Q1 | On plan
2026-09-28¦R04-M01 | 2026-09-28 | R04-M01 | R04 | Points ledger | Committed |  |  |  |  | On plan
2026-09-28¦R04-M03 | 2026-09-28 | R04-M03 | R04 | Pilot group selection | Not committed |  |  |  |  | Not committed
2026-10-05¦R01-M01 | 2026-10-05 | R01-M01 | R01 | One page checkout | Committed | 2026-11-30 | 2026-11-30 |  | MC26Q3 | On plan
2026-10-05¦R01-M02 | 2026-10-05 | R01-M02 | R01 | Saved payment methods | Committed | 2026-12-15 | 2026-12-10 |  | MC26Q3 | On watch
2026-10-05¦R01-M03 | 2026-10-05 | R01-M03 | R01 | Address form speed up | Committed | 2026-10-05 | 2026-10-02 |  | MC26Q3 | On plan
2026-10-05¦R01-M04 | 2026-10-05 | R01-M04 | R01 | Wallet support | Choice point |  |  |  |  | Not committed
2026-10-05¦R01-M05 | 2026-10-05 | R01-M05 | R01 | Express pay button | Committed | 2026-10-14 | 2026-10-14 |  | MC26Q3 | On plan
2026-10-05¦R02-M01 | 2026-10-05 | R02-M01 | R02 | Setup checklist | Committed | 2026-11-20 | 2026-11-27 |  | MC26Q3 | Slipped
2026-10-05¦R02-M02 | 2026-10-05 | R02-M02 | R02 | In app tips | Committed | 2027-01-31 |  |  | MC26Q4 | On hold
2026-10-05¦R02-M03 | 2026-10-05 | R02-M03 | R02 | Starter templates | Not committed |  |  |  |  | Not committed
2026-10-05¦R02-M04 | 2026-10-05 | R02-M04 | R02 | Role picker | Committed | 2026-12-18 |  |  | MC26Q3 | On plan
2026-10-05¦R02-M05 | 2026-10-05 | R02-M05 | R02 | Brand colour audit | Committed | 2026-09-18 |  |  | MC26Q2 | On plan
2026-10-05¦R03-M01 | 2026-10-05 | R03-M01 | R03 | Carrier integration | Committed | 2026-12-10 | 2026-12-10 |  | MC26Q3 | On plan
2026-10-05¦R03-M02 | 2026-10-05 | R03-M02 | R03 | Cut off time logic | Committed | 2027-02-15 | 2027-02-15 |  | MC26Q4 | On plan
2026-10-05¦R03-M03 | 2026-10-05 | R03-M03 | R03 | Delivery promise on product pages | Committed | 2027-03-10 |  |  | MC26Q4 | On plan
2026-10-05¦R03-M04 | 2026-10-05 | R03-M04 | R03 | Region one pilot | Committed | 2026-09-10 | 2026-09-10 |  | MC26Q2 | On plan
2026-10-05¦R03-M05 | 2026-10-05 | R03-M05 | R03 | Third region rollout | Committed | 2027-04-20 |  |  | MC27Q1 | On plan
2026-10-05¦R04-M01 | 2026-10-05 | R04-M01 | R04 | Points ledger | Committed |  |  |  |  | On plan
2026-10-05¦R04-M03 | 2026-10-05 | R04-M03 | R04 | Pilot group selection | Not committed |  |  |  |  | Not committed
2026-10-12¦R01-M01 | 2026-10-12 | R01-M01 | R01 | One page checkout | Committed | 2026-11-30 | 2026-11-30 |  | MC26Q3 | On plan
2026-10-12¦R01-M02 | 2026-10-12 | R01-M02 | R01 | Saved payment methods | Committed | 2026-12-15 | 2026-12-10 |  | MC26Q3 | On watch
2026-10-12¦R01-M03 | 2026-10-12 | R01-M03 | R01 | Address form speed up | Committed | 2026-10-05 | 2026-10-02 | 2026-10-02 | MC26Q3 | Completed
2026-10-12¦R01-M04 | 2026-10-12 | R01-M04 | R01 | Wallet support | Choice point |  |  |  |  | Not committed
2026-10-12¦R01-M05 | 2026-10-12 | R01-M05 | R01 | Express pay button | Committed | 2026-10-14 | 2026-10-14 |  | MC26Q3 | On plan
2026-10-12¦R02-M01 | 2026-10-12 | R02-M01 | R02 | Setup checklist | Committed | 2026-11-20 | 2026-12-04 |  | MC26Q3 | Slipped
2026-10-12¦R02-M02 | 2026-10-12 | R02-M02 | R02 | In app tips | Committed | 2027-01-31 |  |  | MC26Q4 | On hold
2026-10-12¦R02-M03 | 2026-10-12 | R02-M03 | R02 | Starter templates | Not committed |  |  |  |  | Not committed
2026-10-12¦R02-M04 | 2026-10-12 | R02-M04 | R02 | Role picker | Committed | 2026-12-18 |  |  | MC26Q3 | On plan
2026-10-12¦R02-M05 | 2026-10-12 | R02-M05 | R02 | Brand colour audit | Committed | 2026-09-18 |  |  | MC26Q2 | Completed
2026-10-12¦R03-M01 | 2026-10-12 | R03-M01 | R03 | Carrier integration | Committed | 2026-12-10 | 2027-01-14 |  | MC26Q4 | Slipped
2026-10-12¦R03-M02 | 2026-10-12 | R03-M02 | R03 | Cut off time logic | Committed | 2027-02-15 | 2027-02-15 |  | MC26Q4 | On plan
2026-10-12¦R03-M03 | 2026-10-12 | R03-M03 | R03 | Delivery promise on product pages | Committed | 2027-03-10 |  |  | MC26Q4 | On plan
2026-10-12¦R03-M04 | 2026-10-12 | R03-M04 | R03 | Region one pilot | Committed | 2026-09-10 | 2026-09-10 |  | MC26Q2 | On plan
2026-10-12¦R03-M05 | 2026-10-12 | R03-M05 | R03 | Third region rollout | Committed | 2027-04-20 |  |  | MC27Q1 | On plan
2026-10-12¦R04-M01 | 2026-10-12 | R04-M01 | R04 | Points ledger | Committed |  |  |  |  | On plan
2026-10-12¦R04-M03 | 2026-10-12 | R04-M03 | R04 | Pilot group selection | Not committed |  |  |  |  | Not committed

## lkp_People
Name | Role
Priya Sampleton | GPM
Marco Demoso | GPM
Lena Testfield | Lead
Omar Fictiv | Lead
Tove Nomen | Lead
Ravi Placeholder | Lead
Ines Samplewood | Lead

## lkp_ValueChains
Value
Checkout
Onboarding
Fulfilment

## lkp_Steercos
Date | Note
2026-10-21 | First steerco from the portal (assumed date, confirm)
2026-09-16 | Past steerco
2026-11-18
2026-12-16

## lkp_State
Value | Meaning
On track | All committed milestones are forecast on or before their planned date and no High risk is without an action
At risk | At least one committed milestone is slipping or a High risk is open, and the lead believes it is recoverable this quarter
Off track | Commitments for this quarter will be missed without a steerco decision (scope, date or people)

## lkp_MilestoneStatus
Value | Rule | SetBy
Completed | Lead status Completed (done) | Lead
On plan | Committed, forecast on or before planned date, no flag | Calculated
On watch | Committed, forecast on plan, lead flags a concern | Lead
Slipped | Committed, forecast later than planned date | Calculated
On hold | Paused by decision | Lead
Not committed | Commitment is Choice point or Not committed | Calculated

## lkp_LeadStatus
Value | Meaning
Completed | Done; type the Actual date too
On hold | Paused by decision
On watch | Forecast still on plan but you have a concern

## lkp_Commitment
Value | Meaning
Committed | Steerco has agreed to deliver this milestone by its planned date
Choice point | A decision (scope, date, funding or people) is needed before it can be committed
Not committed | A known future need on the horizon, with no promise of date or scope

## lkp_Level
Value | Score
Low | 1
Medium | 2
High | 3

## lkp_OpenClosed
Value
Open
Closed

## lkp_YesNo
Value
Yes
No

## lkp_DecisionState
Value | Meaning
Requested | Raised for steerco, no outcome yet
Decided | Outcome recorded after steerco